## Sheet1
Task Name | Location | User Story | Start Date | End Date | Hours Spent | Notes
Generate Gym mock data | Database | 1 | 2019-02-24 | 2019-02-24 | 1h | Mock data was only partially used in the final implementation. Only a few gyms were implemented
Create search function to find gym | Code | 1 | 2019-02-22 | 2019-02-23 | 6h
Swap new random exercise based on muscle group | Code | 10 | 2019-02-24 | 2019-03-23 | 12h | Implementation took significantly more time than expected. The existing workouts page only implemented the view. I had to create all the backend logic for exercise generation. Then I needed to create a menu for selecting an exercise. Ran into many problems and took significantly longer than expected. Including popup for replace workout
Swap workout exercise with another | Code | 11 | 2019-03-22 | 2019-03-23 | 3h | Initially Ben's task, but I took on since it was integrally related to my implentation of swap new random exercise
Make acceptance test of loaded workout | Code | 8 | 2019-03-24 | 2019-03-24 | >1h | No framework for automatic testing was created. Simply manually running the gherkin scripts was done
Database implementation aid | Code | All | 2019-03-24 | 2019-03-24 | 6h | Decision to switch to a local database, I assisted Samuel in reimplementation of a new database
Meeting participation |  | All | N/A | N/A | 8h total | Attended every meeting, either in person or online.
Contributing to Report | Report |  | 2019-03-30 |  |  | Wrote conclusion: Possible extensions to the project, and story estimation paragraphs