## Sheet1
Task Name | Location | User Story | Start Date | End Date | Hours Spent
Sign Out Acceptance Test | Repository | S5 | 2019-02-24 | (carried over to the end of sprint 2) | 4
Swap exercise with other random exercise | Code | S10 | 2019-02-24 | 2019-02-24 | 6
Database persistence acceptance test | Repository | S6 | 2019-03-21 | 2019-03-23 | 3
Delete Workout Acceptance Test | Repository | S9 | 2019-03-21 | 2019-03-25 | 3
Save Workout acceptance test | Repository | S7 | 2019-03-21 | 2019-03-24 | 3
High User stories acceptance test | Repository | All | 2019-03-23 | 2019-03-25 | 5
Write about Scrum Rituals: Sprint Retrospective | Report |  | 2019-03-30 | 2019-03-31 | 2
write about agile manifesto: working software | report |  | 2019-03-31 | 2019-03-31 | 1.5
write about agile manifesto: sustainable development | report |  | 2019-03-31 | 2019-03-31 | 1.5