## Sheet1
Task Name | Location | User Story | Start Date | End Date | Hours Spent
Design Home View | Code | 5 | 2019-02-12 | 2019-02-12 | 4
Design Saved Workouts View | Code | 8 | 2019-03-18 | 2019-03-19 | 6
Display List of Saved Workouts | Code | 8 | 2019-03-18 | 2019-03-24 | 6
Direct User to Workout View | Code | 8 | 2019-03-18 | 2019-03-20 | 4
No Workouts Error Prompt | Code | 8 | 2019-03-25 | 2019-03-25 | 3
Delete Selected Saved Workout | Code | 9 | 2019-03-22 | 2019-03-24 | 6
Connect Views with DB | Code | All | 2019-03-23 | 2019-03-25 | 8
Refactor DB code to work with app | Code | All | 2019-03-23 | 2019-03-25 | 8
Write about Software Architecture | Report |  | 2019-03-28 | 2019-03-31 | 5
Write about Agile Manifesto; "Deliver working software frequently, from a couple of weeks to a couple of months, with a preference to the shorter timescale" | Report |  | 2019-03-28 | 2019-03-31 | 1