## Sheet1
Task Name | Location | User Story | Start Date | End Date | Hours Spent
Design Muscle Group view | Code | S1 | 2019-02-15 | 2019-02-15 | 6h
Create function to select muscle group | Code | S1 | 2019-02-17 | 2019-02-17 | 6h
Create function to choose number of exercises | Code | S1 | 2019-02-17 | 2019-02-17 | 6h
Setup Repository | Repository | Functional requirement | 2019-02-03 | 2019-02-03 | 4h
Setup Continuous Integration | Repository | Functional requirement | 2019-02-03 | 2019-02-03 | 2h
Management tasks | None | Scrum master | 2019-01-28 | 2019-02-24 | 4h
Setup Code review | Repository | Functional requirement | 2019-02-03 | 2019-02-03 | 2h
Create seperate admin login accounts | Code | S6 | 2019-03-21 | 2019-03-23 | 6h
Add admin ability to modify exercises | Code | S6 | 2019-03-23 | 2019-03-23 | 3h
Display list of available exercise for admin to select | Code | S6 | 2019-03-23 | 2019-03-23 | 3h
Modification saved to exercise database | Code | S6 | 2019-03-24 | 2019-03-24 | 3h
Write about Scrum Rituals : Backlock Grooming, Sprint Planning, Daily Stand-up Meeting, Sprint Demo | Report | - | 2019-03-27 | 2019-03-27 | 2h
Write Scrum Objects : Done Checklist and Sprint Backlog Tasks | Report | - | 2019-03-27 | 2019-03-27 | 2h